## Sheet1
WBS Id | Description | Size | 2012-11-16 | 2012-11-23 | 2012-11-30 | 2012-12-07 | 2012-12-14 | 2012-12-21 | 2012-12-28 | 2013-01-04 | 2013-01-11 | 2013-01-18 | 2013-01-25 | 2013-02-01 | 2013-02-08 | 2013-02-15 | 2013-02-22 | 2013-03-01 | 2013-03-08 | 2013-03-15 | 2013-03-22 | 2013-03-29 | 2013-04-05 | 2013-04-12 | 2013-04-19 | 2013-04-26 | 2013-05-03 | 2013-05-10 | 2013-05-17 | 2013-05-24 | 2013-05-31
2 | Testing of the office(97) cameras and establish the top-20 errors for office (97) cameras. |  | 2012-11-30: 95%; 2013-01-25: 95%; 2013-02-22: 95%; 2013-03-29: 95%
4 | Bug “busting” to increase the MANAGED through-put of office(97) cameras |  | 2012-11-30: 95%; 2013-01-25: 95%; 2013-02-22: 95%; 2013-03-29: 95%
5 | Review of UCF analysis files to create consistency within reports |  | 2012-11-30: 95%; 2013-01-25: 95%; 2013-02-22: 95%; 2013-03-29: 95%
6 | Review of UCF tags in source files to ensure a consistency of naming conventions and appropriate granularity of UCF tags. N.B. granularity is the decision to include top level UCF tags and low-level / verbose UCF tags |  | 2012-11-30: 95%; 2013-01-25: 95%; 2013-02-22: 95%; 2013-03-29: 95%
7 | Add UCF CONTENT tags to all the Office(97) modules |  | 2012-12-21: 5%; 2013-01-25: 25%; 2013-02-22: 50%; 2013-03-29: 95%; 2013-04-26: 100%
8 | UCF Library of basic unit test of its various APIs |  | 2012-11-30: 5%; 2012-12-21: 50%; 2013-01-25: 100%
9 | Regenerate UCF content tags to an XML file (NB: first implementation will save XML tags and content directly to a memory buffer and to a file via the UCF toolset from office PREFILTER calls ) |  | 2012-11-30: 80%; 2012-12-21: 100%
10 | UCF Library Improvements including XML processing (a rough XML camera) |  | 2012-12-21: 100%
11 | UCF Library Improvements including XML processing (XML schema processing back to UCF research) |  | 2013-01-25: 40%; 2013-02-22: 70%; 2013-03-29: 100%
11a | UCF Library proving with the office(97) tags and file content Includes regeneration and xml reports (ANALYSIS LOG, TOKENS OUTPUT) and engineering log. |  | 2013-01-25: 50%; 2013-02-22: 90%; 2013-03-29: 100%
12 | UCF Tokenisation on demand and semantic tree walk processing. |  | 2013-01-25: 50%; 2013-02-22: 70%; 2013-03-29: 95%; 2013-04-26: 100%
13 | Users Quick Start Guide - UCF ( UCF ANALYSIS Tags API ) |  | 2012-12-21: 100%
14 | UCF Software Requirements Update – extend with the use of enumerated tags ids to allow fast look up of string IDs and direct processing of string IDs. Treat this like the registration of PDF names as a set of UCF tags. Then the tags can be grouped either together or as pointers. Note that one way of achieving this is to disallow pointer IDs for the first 64K of addressing space, in which case the pointer will actually refer to a registered enumerated tag value. In this case then a fast look up table may be applied to look up the string ID for the registered string. This also includes the use of data seams and data mines fro fast search in the UCF |  | 2012-11-30: 80%; 2012-12-21: 95%; 2013-02-22: 95%; 2013-03-29: 95%
15 | XML Configure API for PDF (this can be another record type processed by PDF) – This is all part of the future SDK for customers. |  | 2012-11-30: 100%
16 | Database server for Developers (SHEEPDOG style PC + three drives for each data type (.doc,.xls,.ppt) for OFFICE 2003 files and development testing |  | 2012-11-23: 7%; 2012-11-30: 10%; 2012-12-21: 15%; 2013-01-25: 20%; 2013-02-22: 60%
17 | “The Truth Is Out There” test document (OFFICE2003) in native format, XML format and PDF format |  | 2012-11-16: 100%
18 | UCF Office smart token design to support Microsoft Compound File Binary file system. This binary format UCF tokens will be tokenised into UCF tokens by the legacy cameras to a level of granularity which will allow token tree walk to “tag” the tokens and group then in preparation for regeneration into the XML UCF tokens as provided by the reference XML formats for office 2003 |  | 2012-11-16: 50%; 2012-11-23: 100%
19 | Users Quick Start Guide - UCF ( UCF CONTENT Tags API ) |  | 2012-11-16: 95%; 2012-11-23: 100%
20 | MS Office (BINARY) UCF Camera Tokenisation UCF.CFB tokens) software requirements |  | 2012-11-16: 20%; 2012-11-23: 40%; 2012-11-30: 80%; 2012-12-21: 100%
21 | Add UCF CONTENT XML tags to all the office(97) modules |  | 2012-12-21: 1%; 2013-01-25: 5%; 2013-02-22: 20%; 2013-03-29: 40%; 2013-04-26: 60%; 2013-05-31: 90%, completes 28th June
22 | MS Office (BINARY) UCF Camera Tokenisation (UCF.XML tokens) software requirements |  | 2012-11-23: 2%; 2012-11-30: 3%; 2012-12-21: 4%; 2013-01-25: 90%; 2013-02-22: 100%
23 | Render XML to Compound File Binary Tokens for all the office(97) modules |  | 2012-12-21: 2%; 2013-01-25: 5%; 2013-02-22: 40%; 2013-03-29: 80%; 2013-04-26: 100%
24 | Render Compound File Binary Tokens to XML for all the office(97) modules |  | 2012-12-21: 2%; 2013-01-25: 5%; 2013-02-22: 20%; 2013-03-29: 50%; 2013-04-26: 100%
25 | PDF Camera GWFile API for customers memory leak issue |  | 2012-11-16: 100%
26 | Glasswall SDK for customers centred around file formats (.PDF, .JPEG, .PNG, .GIF) |  | 2012-11-23: 10%; 2012-11-30: 30%; 2012-12-21: 50%; 2013-01-25: 100%
27 | PDF Camera Software Maintenance – top 20 bug busting and issues |  | 2012-11-23: 96%; 2012-11-30: 98.15%; 2012-12-21: 98.45%; 2013-02-22: 97%